## Risk Tracking Template
Risk Tracking Template
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Inadequate training data | Reduced accuracy in detection | Augment dataset with diverse examples | Medium | Project Manager | Ensure diversity in dataset to improve model performance
2 | Different regions has different sign languages | Inaccurate detection or no detection | Dataset trained on multiple sign languages | High | Project Manager | Train Data on the most popular sign languages
3 | Limited hardware resources | Slow processing times or inability to handle large datasets | Upgrade hardware resources or optimize algorithms | High | IT Administrator
4 | Environmental factors | Decreased accuracy due to lighting, background clutter, or noise | Implement robust preprocessing techniques | Medium | Software Developer
5 |  |  |  |  | Data Protection Officer
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## How to Use this Template
Introduction
A risk tracking template allows you to identify and track any risks that might appear in your project. It's critical to track risks in your projects, so they don't become issues that derail progress. A risk tracking template is a living document, and should be frequently inspected and updated.
Definition of Terms
ID: The identification number of your risk.
Description of Risk: Provide a brief description of your risk that anyone can understand.
Impact: Outline the potential impact that risk can have on your project.
Risk Response: Describe what your reaction to the risk is, in order to quell it.
Risk Level: Define the priority of the risk; how likely it is to affect your project.
Risk Owner: Define the team member or manager in charge of monitoring the risk.
Notes: Add any notes you may have for a better understanding of the risk. Update regularly.